## 1. Setup & Recap
Scenario cost data | [5 empty] | $ or % | Remarks |  |  |  | Instructions:
1. Fill in yellow cells with your company information and project information below.
| Crew size (# people) |  |  |  |  | 6 |  |  |  |  | 2. Do not write over red cells as they contain formulas.
| Crew average wage (CAW) |  |  |  |  | 23 |  |  |  |  | 3. Change the descriptions as necessary.
| Man-hours per man per day |  |  |  |  | 10 |  |  |  |  | 4. Be sure to save and back up your worksheet.
| Overtime factor (OTF) |  |  |  |  | 10% | 40 hours per week |  |  |  | 5. Go to sheet 2-A on the tab at the bottom of this page to input your production information.
| Risk factor (RF) |  |  |  |  | 12% |  |  |  |  | 6. Go to sheet 3 on the tab at the bottom of this page to input your general conditions information.
| Crew average wage w/OTF & RF |  |  |  |  | 28.06
| Labor burden |  |  |  |  | 28.5% |  |  |  |  | Date:
| Sales tax |  |  |  |  | 8.25% |  |  |  |  | Project:
| G&A overhead per hour (OPH) |  |  |  |  | 21.45 |  |  |  |  | Location:
| Net profit margin |  |  |  |  | 25% |  |  |  |  | P.O.C./G.C.:
| Crew truck with trailer |  |  |  |  | 12 |  |  |  |  | Phone / Fax:
| Curb time man-hours |  |  |  |  | 515 |  |  |  |  | Due Date:
| Total Days to complete Job |  |  |  |  | 9
| Number of units |  |  |  |  | 1 | LS |  |  |  | Estimator: | Hayden Lutz, Rob McKenna, John Dickinson
Scenario |  | Materials |  | Labor |  | Equipment |  | Subcontractors |  | Subtotals
I. Production or "Curb" time costs
|  | 28583.59 |  | 11845 |  | 2362.9 |  | 59986
|  | 28583.59 |  | 11845 |  | 2362.9 |  | 59986 |  | 102777.49
II. General conditions (off-site or non-curb-time costs)
|  | 40 |  | 3225 |  | 1140 |  | 0
|  | 40 |  | 3225 |  | 1140 |  | 0 |  | 4405
| Subtotals | 28623.59 |  | 15070 |  | 3502.9 |  | 59986 |  | 107182.49
III. Margins & markups
| A.Sales tax | 2361.4462
| B.Labor burden |  |  | 4294.95
| Subtotals | 30985.0362 |  | 19364.95 |  | 3502.9 |  | 59986
| Total direct costs (TDC) | [6 empty] | 113838.8862 | TDC
C. G&A overhead costs
| 625.1 | (Number of man-hours x OPH) |  |  |  | 21.45 | = | 13408.395
| BEP (TDC + G&A overhead) | [6 empty] | 127247.2812 | BEP
D. Contingency factor (if desired)
E. Net profit margin
| 25% | [6 empty] | 42415.7604
| F. Total price | [6 empty] | 169663.0416
-
IV. Scenario analysis
A. Unit price (Total price ÷ units)
|  | 169663.0416 | divided by |  | 1 | = |  | 169663.0416 | Curb-time rate
B. Sales or revenue per man-hour (Total price ÷ all man-hours)
|  | 169663.0416 | divided by |  | 625.1 | = |  | 271.4174 | Portal-to-portal rate
C. Gross profit margin ((G&A overhead + Net profit) ÷ Total price)
|  | 55824.1554 |  | ÷ | 169663.0416 | = |  | 32.9% | GPM
V. Ratio and per hour analysis: $
|  |  |  | % |  |  |  | $/RATIO
| A. SPH: | 271.4174 |  | 100% |  | J. Mat/Lab: |  | 1.8994 | GPM
| B. DCPH: | 182.1131 |  | 67.1% |  | K. MPH: |  | 45.7904 | 16.87%
| C. OPH: | 21.45 |  | 7.903% |  | L. Eq/Lab: |  | 0.23244 | :1
| D. PPH: | 67.8544 |  | 25% |  | M. EqPH: |  | 5.6037 | 2.065%
| E. BEP: | 127247.2812 |  | 75% |  | N. GC: |  | 4405 | 2.596%
| F. G&A Ovhd: | 13408.395 |  | 7.903% |  | O. GCPH: |  | 7.0469 | 2.596%
| G. NPM: | 42415.7604 |  | 25% |  | P. GCH/TH: |  |  | 0%
| H. GPM: | 55824.1554 |  | 32.9% |  | Q. Material Factor: |  | 5.9274 | x Material Cost
| I. GPMPH: | 89.3044 |  | 32.9% |  | R. Unit Price: |  | 169663.0416
VI. MORS percentage markup on labor + burden (assuming a 10, 25 & 5% markup on mat'l, equip. & subs) | [9 empty] | 34.45%

## Landscape Intallation
| Project: | Date:
| Location: | Estimator: | Hayden Lutz, Rob McKenna, John Dickinson |  | CAW Loaded | 28.06
| P.O.C./G.C.: | Crew Size: | 6
| Phone / Fax: | Hours/Day: | 10
| Due Date: | CAW: | 23 |  | Phase 1 | Quantity | Unit
| Type Work: | Risk Factor | 12% |  | Total Labor Hrs | 498.1 | Hrs L
|  | OT Factor | 10%
|  | Column Calcualtions |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
# | Description | Quantity | Unit | Unit Cost | Material | Labor | Equip | Subs
| TOTALS |  |  |  | 26873.59 | 11456.3 | 2338 | 59986
Materials
| Flagstone Stepping Stones | 10 | Each | 23 | 230
| Tumbled Paving Stones (Patio) | 788 | Sq. Ft. | 4.75 | 3743
| Paving Stone Border | 385 | Lin. Ft. | 5 | 1925
| Flagstone Porch (Overlay) | 51 | Sq. Ft. | 5.25 | 267.75
| Exposed Aggregate Concrete Mix | 10 | Cu. Yd. | 165 | 1650
| Armour Stone Outcropping | 8 | Tons | 215 | 1720
| Armour Stone Boulders (Deco) | 5 | Each | 118 | 590
| Natural Stone Garden Wall | 1.5 | Tons | 300 | 450
| CELTIK Stone Steps | 10 | Each | 95 | 950
| River Stone (Decorative) | 2 | Tons | 48.67 | 97.34
| Wood Landing & Steps Material | 43 | Sq. Ft. | 15 | 645
| Black Vinyl Chainlink Fence | 200 | Lin. Ft. | 11 | 2200
| Wood Fence (Gate Section) | 8 | Lin. Ft. | 18.5 | 148
| Road Base (Crushed Concrete) | 30 | Tons | 35 | 1050
| Bedding Sand (Concrete Sand) | 5 | Tons | 45 | 225
| Polymeric Sand (Joints) | 12 | Bags | 45 | 540
| Snap-Edge Paver Restraints | 385 | Lin. Ft. | 2.5 | 962.5
| Rebar (#3) & Wire Mesh | 40 | Sticks | 12 | 480
| Drainage Rock (#57 Stone) | 2 | Tons | 55 | 110
| Marles Doublefile Viburnum | 5 | Each | 30 | 150
| Dwarf Japanese Garden Juniper 40cm | 1 | Each | 30 | 30
| Old Gold Juniper 40cm | 3 | Each | 30 | 90
| Annabelle Hydrangea 2 GAL | 3 | Each | 25 | 75
| Fairview Dwarf Yew 40cm | 8 | Each | 35 | 280
| Anthony Waterer Spirea 50cm | 7 | Each | 28 | 196
| Canadale Gold Euonymus 40cm | 1 | Each | 30 | 30
| Hughes Juniper 40cm | 1 | Each | 30 | 30
| Green Gem Boxwood 30cm | 11 | Each | 28 | 308
| Gold Mound Spirea 40cm | 4 | Each | 28 | 112
| Early Cotoneaster 40cm | 6 | Each | 30 | 180
| Emerald Gaiety Euonymus 40cm | 4 | Each | 30 | 120
| Golden Variegated Dogwood 50cm | 1 | Each | 32 | 32
| Calgary Carpet Juniper 40cm | 6 | Each | 30 | 180
| Pee Gee Hydrangea 50cm | 1 | Each | 32 | 32
| Purple Smoke Bush 50cm | 1 | Each | 35 | 35
| Snowmound Spirea 50cm | 5 | Each | 28 | 140
| Golden Mockorange 50cm | 1 | Each | 30 | 30
| Blue Chip Juniper 40cm | 1 | Each | 30 | 30
| Red Jade Weeping Crabapple 45mm | 1 | Each | 185 | 185
| Dr. Merrill Star Magnolia 175cm | 1 | Each | 165 | 165
| Shubert Chokecherry 50mm | 1 | Each | 180 | 180
| Emerald Pyramidal Cedar 150cm | 2 | Each | 120 | 240
| Fraser Fir 200cm | 1 | Each | 180 | 180
| Serviceberry Clump 175cm | 1 | Each | 160 | 160
| Chanticleer Flowering Pear 50mm | 1 | Each | 190 | 190
| Mulch (50lbs bag) | 200 | Bags | 10 | 5510
Labor
| Flagstone Stepping Stones (Excavate & Set) | 7.5 | Hrs L | 23 |  | 172.5
| Tumbled Pavers (Screed, Lay, Cut, Compact) | 94.6 | Hrs L | 23 |  | 2175.8
| Paver Border (Soldier Course - Cutting/Setting) | 38.5 | Hrs L | 23 |  | 885.5
| Flagstone Porch (Mortar Overlay Installation) | 20.4 | Hrs L | 23 |  | 469.2
| Exposed Aggregate Concrete (Form, Pour, Wash)** | 114.8 | Hrs L | 23 |  | 2640.4
| Armour Stone Outcropping (Machine Set***) | 13.5 | Hrs L | 23 |  | 310.5
| Armour Stone Boulders (Placement) | 2.5 | Hrs L | 23 |  | 57.5
| Natural Stone Garden Wall (Stacking) | 22.8 | Hrs L | 23 |  | 524.4
| CELTIK Stone Steps (Base Prep & Set) | 15 | Hrs L | 23 |  | 345
| River Stone (Spreading) | 2 | Hrs L | 23 |  | 46
| Wood Landing & Steps (Carpentry/Assembly) | 21.5 | Hrs L | 23 |  | 494.5
| Black Vinyl Chainlink Fence (Auger & Install) | 40 | Hrs L | 23 |  | 920
| Wood Fence Gate (Post Set & Hang) | 6 | Hrs L | 23 |  | 138
| General Excavation & Base Install (30 Tons) | 18 | Hrs L | 23 |  | 414
| Shrub Installation (Excavate Plant Backfill) | 35 | Hrs L | 23 |  | 805
| Tree Installation (Excavate Plant Stake) | 16 | Hrs L | 23 |  | 368
| Mulch installation | 30 | Hrs L | 23 |  | 690
Equipment
| Skid Steer Loader | 18 | HR | 38.5 |  |  | 693
| Plate Compactor | 8 | HR | 8.5 |  |  | 68
| Masonry/Demo Saw | 10 | HR | 12 |  |  | 120
| Skid Steer / Mini-Ex | 14 | HR | 42 |  |  | 588
| Concrete Mixer | 6 | HR | 6.5 |  |  | 39
| Mini Excavator + Auger | 8 | HR | 55 |  |  | 440
| Delivery Truck / Trailer | 6 | HR | 65 |  |  | 390
SUBCONTRACTORS
| Pool Installation | 1 | Job | 55575 |  |  |  | 55575
| Paving Installation | 1 | Job | 2657 |  |  |  | 2657
| Decking Installation | 1 | Job | 1754 |  |  |  | 1754

## Lawn Installation
| Project: | Date:
| Location: | Estimator: | Hayden Lutz, Rob McKenna, John Dickinson |  | CAW Loaded | 28.06
| P.O.C./G.C.: | Crew Size: | 6
| Phone / Fax: | Hours/Day: | 10
| Due Date: | CAW: | 23 |  | Phase 1 | Quantity | Unit
| Type Work: | Risk Factor | 12% |  | Total Labor Hrs | 16.9 | Hrs L
|  | OT Factor | 10%
|  | Column Calcualtions |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
# | Description | Quantity | Unit | Unit Cost | Material | Labor | Equip | Subs
| TOTALS |  |  |  | 1710 | 388.7 | 24.9 | 0
| Materials |  |  |  | 0
| Palisades Zoysia Sod (450 sq. ft. per pallet) | 3 | Pallet | 335 | 1005
| Delivery Fee (Flat Rate - Sod Farm) | 1 | LS | 175 | 175
| Bulk Garden Mix / Premium Topsoil | 8 | CY | 45 | 360
| Delivery Fee (Bulk Soil Dump Truck) | 1 | LS | 125 | 125
| Starter Fertilizer (High Phosphorus) | 1 | Bag | 45 | 45
| Labor |  |  |  |  | 0
| Spread Topsoil (Wheelbarrow) | 1.2 | Hrs L | 23 |  | 27.6
| Fine Grading (Hand Rake) | 13.5 | Hrs L | 23 |  | 310.5
| Lay Sod (St. Aug/Zoysia) | 1.2 | Hrs L | 23 |  | 27.6
| Fertilizer Application (Rotary) | 1 | Hrs L | 23 |  | 23
Equipment
| Handtools | 24.9 | HR | 1 |  |  | 24.9

## 2-C. Production costs
| Project: | Date:
| Location: | Estimator: | Hayden Lutz, Rob McKenna, John Dickinson |  | CAW Loaded | 28.06
| P.O.C./G.C.: | Crew Size: | 6
| Phone / Fax: | Hours/Day: | 10
| Due Date: | CAW: | 23 |  | Phase 1 | Quantity | Unit
| Type Work: | Risk Factor | 12% |  | Total Labor Hrs | 0 | Hrs L
|  | OT Factor | 10%
|  | Column Calcualtions |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
# | Description | Quantity | Unit | Unit Cost | Material | Labor | Equip | Subs
| TOTALS |  |  |  | 0 | 0 | 0 | 0
| Materials | 0 | EA | 1 | 0
|  | 0 | EA | 1 | 0
|  | 0 | EA | 1 | 0
|  | 0 | EA | 1 | 0
|  | 0 | EA | 1 | 0
|  | 0 | EA | 1 | 0
0
| Labor | 0 | Hrs L | 28.06 |  | 0
|  | 0 | Hrs L | 28.06 |  | 0
|  | 0 |  |  |  | 0
| Equipment | 0 | HR | 1 |  |  | 0
|  | 0 | HR | 1 |  |  | 0

## 3. GC costs
| Project: |  |  | Date:
| Location: |  |  | Estimator: | Hayden Lutz, Rob McKenna, John Dickinson |  | CAW Loaded | 28.06
| P.O.C./G.C.: |  |  | Crew Size: | 6
| Phone / Fax: |  |  | Hours/Day: | 10
| Due Date: |  |  | CAW: | 23 |  | Phase 2 | Quantity | Unit
| Type Work: | General conditions |  | Risk Factor | 12% |  | Total Labor Hrs | 127 | Hrs L
|  |  |  | OT Factor | 10%
|  |  |  | Column Calcualtions |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!
# | Description |  |  | Quantity | Unit | Unit Cost | Material | Labor | Equip | Subs
| TOTALS |  | hr/day |  |  |  | 40 | 3225 | 1140 | 0
| Superintendent (1 hour per day) |  | 1 | 9 | Hrs L | 45 |  | 405
| Superintendent Truck |  | 1 | 9 | Hrs | 45 |  |  | 405
| Foreman admin time (1 Hr / Day) |  | 1 | 9 | Hrs L | 35 |  | 315
| Crew Truck (8 hrs/day) |  | 8 | 72 | Hrs | 10 |  |  | 720
| Drive Time (1 hr/day / man) |  | 1 | 54 | Hrs L | 23 |  | 1242
| Load / Unload Time (1 hr/day/man) |  | 1 | 54 | Hrs L | 23 |  | 1242
| Dump Fees ($40 per trip) |  | N/A | 1 | LS | 40 | 40
| Warranty Labor |  | N/A | 1 | Hrs L | 21 |  | 21
| Warranty Equipment |  | N/A | 1 | Hrs | 15 |  |  | 15